## UT IT
SL | UT INFO TECH (IT) SYSTEMS | COST | SCOPE | EFFORT | DURATION
1 | WEBSITE | RS . 80,000 | Static corporate website (5–8 pages) Responsive design (Mobile, Tablet, Desktop) Clean UI/UX design aligned with brand Contact form (email integration) SEO-friendly structure (basic on-page SEO) Performance optimized (fast load) Hosting deployment & domain linking Basic security setup (HTTPS) | 1 UI/UX Designer(100%), 1 Frontend Developer(100%) | 1 WEEK
2 | WORKING SITE | RS . 5,50,000 | User Roles * Admin * Sales * Counsellor * User Core Functionalities * User registration with Email + WhatsApp welcome message * Auto-generated User ID & Enquiry ID * Enquiry → Lead → Proposal → Payment → Process flow * Admin dashboard: * Pending / Assigned / Closed enquiries * Counsellor assignment * Discount management * Sales module: * Lead buckets * Proposal creation & sharing * Counsellor module: * Assigned cases * Session notes & recordings * Auto-delete recordings after 2–3 days (from counsellor view) * User module: * View proposals * Make online payments (advance + remaining) * Activity history & reports * Feedback submission (visible to Admin only) * Payment system: * Online payment gateway * Advance & final payment handling * Reports & analytics: * Dummy reports initially * User-wise & role-wise activity reports * Promotions & notifications (admin-controlled) * Subscription-ready architecture (future-ready) * Franchise enquiry form (apply → admin review) ❌ No public-facing UI ❌ Internal & controlled access only | 1 UI/UX Designer(50–60%), 1 Frontend Developer(100%), 1 Backend Developer(100%), 1 QA(30–40%) | 7 to 8 WEEKS
3 | WHATS APP | RS . 1,00,000 | WhatsApp Business API Setup * WhatsApp Business API configuration * Template approval & setup * Phone number verification Automated Messages * Welcome message on user registration * Enquiry confirmation with Enquiry ID * Proposal shared notification * Payment confirmation (advance & final) * Status updates (Assigned / In Progress / Closed) * Promotional broadcasts (admin-triggered) System Integrations * Integration with Website & Working Site * Trigger-based messaging from system actions * Admin control to enable/disable messages Admin Controls * Template management * Message logs & delivery status * Broadcast control (limited & compliant) ❌ No chatbot AI ❌ No free WhatsApp usage (API is paid) | 1 Backend Developer(100%), 1 Testing & Deployment(40%-50%) | 1 WEEK
4 | EVOLVE APP | RS . 5,00,000 | User App * Login / Registration * View enquiry → proposal → payment flow * Online payment (advance & balance) * View reports & activity history * Notifications (status, reminders) * Feedback submission Counsellor App * Login * Assigned users list * Session updates & notes * Temporary recording upload * Status updates Common Features * Secure authentication * Role-based access * API integration with Working Site * Push notifications * Basic analytics & logs ❌ No AI chatbot ❌ No offline-first heavy sync ❌ No advanced admin controls (can be Phase-2) | 1 UI/UX Designer(50%), 1 Mobile App Developer(100%), Backend/API Support (40%), 1 QA & Testing(40%) | 8 to 9 WEEKS
5 | SOCIAL MEDIA SITES : INSTA, FB, LINKEDIN, YOUTUBE, GOOGLE, SERVICES TPT | RS ? | TBD | RESOURCES ? | WEEKS ?
6 | SOFTWARE'S | RS ? | TBD | RESOURCES ? | WEEKS ?
7 | HARDWARE'S | RS ? | N/A | RESOURCES ? | WEEKS ?
8 | ERP | RS 5,50,000 | Scope of Work – ERP System * Design and development of a custom ERP system to manage core business operations * User & role management with role-based access control * CRM & lead management covering enquiry, proposal, and customer lifecycle * Finance & payment management including invoices, advance & balance tracking * Operations management for task allocation, status tracking, and workflow control * Reports & dashboards for management and performance monitoring * System integrations with website, working site, mobile app, WhatsApp, and payment gateway * Security, audit logs, and data backup implementation * Deployment, testing, and basic user training Scope of Work – ERP System * Design and development of a custom ERP system to manage core business operations * User & role management with role-based access control * CRM & lead management covering enquiry, proposal, and customer lifecycle * Finance & payment management including invoices, advance & balance tracking * Operations management for task allocation, status tracking, and workflow control * Reports & dashboards for management and performance monitoring * System integrations with website, working site, mobile app, WhatsApp, and payment gateway * Security, audit logs, and data backup implementation * Deployment, testing, and basic user training | 1 Backend Developer(100%), 1 Frontend Developer(100%), 1 QA / Tester(50%) | 10–12 WEEKS